# Project Planning Phase - UCAB MERN Cab Booking System

Project Name: UCAB – MERN Stack Cab Booking System
Team Members: Pavan Sri Ambikesh Pilli (Lead), Govvala Harika Deepthi, Sayan Kar, Vamsi Meesala, Suvarna Ratnam Naradala

## Product Backlog & Sprint Planning

| Sprint | Epic | USN | User Story | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | Register using name, email and password | 2 | High | Suvarna, Deepthi |
| Sprint-1 | Registration | USN-2 | Receive registration confirmation | 1 | High | Suvarna |
| Sprint-1 | Login | USN-3 | Login using email and password | 2 | High | Deepthi |
| Sprint-1 | Dashboard | USN-4 | Access dashboard after login | 2 | High | Pavan |
| Sprint-2 | Cab Booking | USN-5 | Enter pickup and drop locations | 3 | High | Vamsi |
| Sprint-2 | Cab Booking | USN-6 | View available cabs | 3 | High | Sayan |
| Sprint-2 | Fare | USN-7 | View estimated fare | 2 | Medium | Suvarna |
| Sprint-2 | Booking | USN-8 | Confirm booking | 3 | High | Deepthi |
| Sprint-3 | History | USN-9 | View booking history | 2 | Medium | Pavan |
| Sprint-3 | Profile | USN-10 | Update profile | 2 | Medium | Suvarna |
| Sprint-3 | Payments | USN-11 | Online payments | 3 | High | Vamsi |
| Sprint-3 | Tracking | USN-12 | Track cab in real time | 5 | High | Sayan |
| Sprint-4 | Admin | USN-13 | Manage users | 3 | High | Pavan |
| Sprint-4 | Admin | USN-14 | Manage bookings | 3 | High | Deepthi |
| Sprint-4 | Reports | USN-15 | View reports | 2 | Medium | Suvarna |
| Sprint-4 | Notifications | USN-16 | Booking notifications | 2 | Medium | Vamsi |
| Sprint-4 | Offers | USN-17 | View offers | 2 | Low | Sayan |
| Sprint-4 | Feedback | USN-18 | Ride feedback | 2 | Medium | Suvarna |
| Sprint-4 | Logout | USN-19 | Secure logout | 1 | High | Deepthi |

## Project Tracker

| Sprint | Points | Duration | Start | Planned End | Completed | Release |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 15 Feb 2025 | 20 Feb 2025 | 20 | 20 Feb 2025 |
| Sprint-2 | 20 | 6 Days | 21 Feb 2025 | 26 Feb 2025 | 20 | 26 Feb 2025 |
| Sprint-3 | 20 | 6 Days | 27 Feb 2025 | 4 Mar 2025 | 20 | 4 Mar 2025 |
| Sprint-4 | 20 | 6 Days | 5 Mar 2025 | 10 Mar 2025 | 20 | 10 Mar 2025 |

## Velocity

Velocity = 20 story points / 6 days = 3.33 story points per day.

## Burndown Chart Data

| Day | Remaining Story Points |
| --- | --- |
| 1 | 20 |
| 2 | 17 |
| 3 | 14 |
| 4 | 10 |
| 5 | 6 |
| 6 | 0 |